## RACI Matrix
Passkey Rollout — RACI Matrix
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Activity | Security | IT | Helpdesk | Comms | Legal / HR | Project Mgmt | Exec Sponsor | Notes
PLANNING
Define passkey architecture & storage model | R/A | C |  |  |  | I | I | Device-bound vs synced, IdP selection
Assess device & OS compatibility | C | R/A |  |  |  | I |  | Inventory all platforms including BYOD
Identify compliance requirements | R | C |  |  | C | I | I | Regulatory, privacy, union considerations
Select passkey solution / vendor | R/A | R |  |  | C | I | A
Define exception policy (VMs, VDI, shared devices) | R/A | R | C |  |  | I |  | Document and review regularly
Establish rollback criteria | R | R/A |  |  |  | I | I
PILOT / EARLY ADOPTERS
Recruit cross-functional early adopters | C | R |  | R |  | A |  | Not just security enthusiasts
Build automated onboarding flow | C | R/A |  |  |  | I |  | Manual onboarding does not scale
Develop self-service testing tool | C | R/A |  |  |  | I |  | Let users verify setup before cutover
Write support scripts & train helpdesk | C | R | R/A |  |  | I |  | Cover all major OS platforms
Create user-facing FAQ & documentation | C | C | C | R/A |  | I |  | Intranet, email, manager briefings
Run pilot and collect feedback | R | R | R | I |  | A | I | Address feedback before expanding
BROAD ROLLOUT
Communicate timeline and expectations | C | C |  | R/A |  | I | I | Clear deadlines, no surprises
Enable passkeys for new hires by default | C | R/A |  |  | I | I |  | Can precede broad rollout
Phase rollout by department / region | C | R/A | R | R |  | A | I
Disable legacy auth: plan and 90-day deprecation notice | R/A | R |  | C |  | I | A | Separate workstream; prevents downgrade attacks
Disable legacy auth: incremental rollout (1% → 10% → 50% → 100%) | R/A | R | R | C |  | A | I | Go/No-Go gate at each increment
Disable legacy auth: end grace period and full retirement | R/A | R | I | C |  | A | I | Monitor support volume post-retirement
Monitor adoption dashboard | I | R |  |  |  | R/A | I
Run office hours for user support | C | R | R/A |  |  | I
ONGOING
Manage device lifecycle (new laptop, new phone) | C | R/A | R |  |  | I |  | Clear re-enrollment process
Offboard employees (revoke passkeys) | C | R/A |  |  | I |  |  | Normal JML processes apply
Review exceptions and reduce over time | R/A | R |  |  |  | I | I
Track emerging standards (DPoP, machine identity) | R/A | C |  |  |  | I | I

## Rollout Tracker
Passkey Rollout — Milestone Tracker
Update status as you progress. Adapt milestones to your organization.
Phase | # | Milestone | Owner | Target Date | Actual Date | Status | Notes / Blockers
Pre-requisites | 0.1 | Device & OS inventory completed |  |  |  | Not Started | Focus exercise on understanding most common device types to preempt and potential TPM/Secure enclave compatibility issues
Pre-requisites | 0.2 | Identity provider passkey support confirmed |  |  |  | Not Started | All modern SaaS identity providers (e.g., Okta, EntraID) support passkeys
Pre-requisites | 0.3 | Compliance review completed |  |  |  | Not Started
Pre-requisites | 0.4 | Exception policy defined (VMs, VDI, shared devices) |  |  |  | Not Started
Pre-requisites | 0.5 | Rollback plan documented |  |  |  | Not Started
Pre-requisites | 0.6 | Go / No-Go decision |  |  |  | Not Started
PILOT
Pilot | 1.1 | Early adopter cohort recruited (cross-functional) |  |  |  | Not Started | Ensure all functions and levels in the org are suffciently represented
Pilot | 1.2 | Automated onboarding flow built and tested |  |  |  | Not Started
Pilot | 1.3 | Self-service testing tool available |  |  |  | Not Started
Pilot | 1.4 | Support scripts written and helpdesk trained |  |  |  | Not Started
Pilot | 1.5 | User-facing FAQ and documentation published |  |  |  | Not Started
Pilot | 1.6 | Pilot launched |  |  |  | Not Started
Pilot | 1.7 | Pilot feedback collected and addressed |  |  |  | Not Started
Pilot | 1.8 | Go / No-Go for broad rollout |  |  |  | Not Started
BROAD ROLLOUT
Broad Rollout | 2.1 | Communications sent (timeline, expectations, benefits) |  |  |  | Not Started
Broad Rollout | 2.2 | New hires passkey-first by default |  |  |  | Not Started
Broad Rollout | 2.3 | Phase 1 departments enrolled |  |  |  | Not Started
Broad Rollout | 2.4 | Phase 2 departments enrolled |  |  |  | Not Started
Broad Rollout | 2.5 | Phase 3 departments enrolled (full org) |  |  |  | Not Started
Broad Rollout | 2.6 | Legacy auth methods disabled |  |  |  | Not Started | Prevents downgrade attacks (Example: https://www.proofpoint.com/us/blog/threat-insight/dont-phish-let-me-down-fido-authentication-downgrade)
Broad Rollout | 2.7 | Adoption dashboard reviewed — target met |  |  |  | Not Started
LEGACY RETIREMENT
Legacy Retirement | 3.1 | Legacy auth retirement plan documented and approved |  |  |  | Not Started | Separate workstream from passkey rollout
Legacy Retirement | 3.2 | Comms: deprecation notice sent (90-day warning) |  |  |  | Not Started | Email, partner comms, in-app banner
Legacy Retirement | 3.3 | Support trained on migration workflow and escalations |  |  |  | Not Started
Legacy Retirement | 3.4 | Internal testing: legacy auth disabled for project team |  |  |  | Not Started | Validate migration flow end-to-end
Legacy Retirement | 3.5 | Go / No-Go: 1% rollout |  |  |  | Not Started | Explicit gate before each increment
Legacy Retirement | 3.6 | Legacy auth disabled: 1% of accounts |  |  |  | Not Started | Monitor support tickets and rollback triggers
Legacy Retirement | 3.7 | Go / No-Go: 10% rollout |  |  |  | Not Started | Review metrics from 1% before proceeding
Legacy Retirement | 3.8 | Legacy auth disabled: 10% of accounts |  |  |  | Not Started
Legacy Retirement | 3.9 | Go / No-Go: 50% rollout |  |  |  | Not Started
Legacy Retirement | 3.1 | Legacy auth disabled: 50% of accounts |  |  |  | Not Started
Legacy Retirement | 3.11 | Go / No-Go: 100% rollout |  |  |  | Not Started | Final gate — confirm no critical blockers
Legacy Retirement | 3.12 | Legacy auth disabled: 100% of accounts |  |  |  | Not Started | Prevents downgrade attacks
Legacy Retirement | 3.13 | Grace period ended — legacy methods fully retired |  |  |  | Not Started | Monitor and support post-retirement
STEADY STATE
Steady State | 4.1 | Device lifecycle processes documented |  |  |  | Not Started | New laptop, new phone, lost device
Steady State | 4.2 | Offboarding process updated for passkeys |  |  |  | Not Started | If users are allowed to keep passkey mechanism, tell them what functionality will change post-offboarding
Steady State | 4.3 | Exception list reviewed and reduced |  |  |  | Not Started | Quarterly review
Steady State | 4.4 | Post-rollout retrospective completed |  |  |  | Not Started

## Readiness Checklist
Passkey Rollout — Readiness Checklist
Complete before each phase gate. Status: Not Started / In Progress / Completed / Blocked
Category | Checklist Item | Status | Owner | Notes
TECHNICAL
Technical | All target platforms tested (Windows, macOS, iOS, Android) | Not Started
Technical | BYOD devices accounted for (alternatives for non-mobile users) | Not Started
Technical | VM / VDI exceptions identified and fallback auth defined | Not Started
Technical | Automated onboarding flow tested end-to-end | Not Started
Technical | Self-service setup verification tool available | Not Started
Technical | Legacy auth disable plan tested in staging | Not Started
Technical | Rollback procedure tested | Not Started
Technical | Platform limits documented (max passkeys, max auth methods per user) | Not Started |  | Check IdP documentation for limits
SUPPORT
Support | Helpdesk trained on passkey troubleshooting (all OS) | Not Started
Support | Support scripts written and reviewed | Not Started
Support | Escalation paths defined and documented | Not Started
Support | Intranet documentation published | Not Started
Support | Office hours scheduled for rollout period | Not Started
Support | Helpdesk trained on full trust re-establishment process (e.g., out-of-band identity verification via video call with user’s manager before MFA reset) | Not Started |  | Define identity verification steps before rollout and document who can authorize a reset
COMMUNICATIONS
Communications | Announcement comms drafted and approved | Not Started
Communications | All comms reviewed against quality criteria | Not Started |  | Check each: - Benefits framing emphasizes user experience, not just security - Timeline and deadlines are clearly stated - Past auth changes are acknowledged where relevant - Support contact info is included - Instructions are clear and concise with expected UX described
Communications | Deprecation notice sent with 90-day lead time | Not Started |  | Required before disabling legacy auth
Communications | In-app prompts or banners launched to encourage passkey setup | Not Started |  | WhatFix, Pendo, or native UI
Communications | Partner / external user comms sent (if applicable) | Not Started
Communications | Reminder comms scheduled at 60-day and 30-day marks | Not Started
Communications | Adoption metrics shared with leadership regularly | Not Started
GOVERNANCE
Governance | Executive sponsor identified and briefed | Not Started
Governance | Go / No-Go criteria defined for each phase | Not Started
Governance | Adoption metrics and dashboard in place | Not Started
Governance | Legal / HR consulted on BYOD and biometric implications | Not Started
Governance | Exception policy documented and approved | Not Started
LIFECYCLE
Lifecycle | New laptop re-enrollment process documented | Not Started
Lifecycle | New phone re-enrollment process documented | Not Started
Lifecycle | Lost / stolen device revocation process tested | Not Started
Lifecycle | Offboarding updated to include passkey decommission | Not Started
Lifecycle | Temp worker / contractor process defined (if applicable) | Not Started

## Support Scenarios
Passkey Rollout — Common Support Scenarios
For support staff handling passkey-related tickets. Role labels (User / Helpdesk / Admin) are illustrative — map to your organization’s support tiers and escalation paths. Adapt resolution steps to your identity provider and platform.
Category | User Reports | Impact | Resolution Steps | Escalate If | Prevention / Training
DEVICE LIFECYCLE
New phone | “I got a new phone, and it says no passkeys are available when I log in” | Medium | 1. Helpdesk: confirm user has a second registered method (laptop passkey or physical key) 2. User: log in from laptop 3. User: navigate to identity provider security settings 4. User: register new passkey on new phone 5. User: verify new passkey works | User has no second method and is fully locked out → Admin: MFA reset required | Educate users to always register at least two methods (laptop + mobile). Include in onboarding docs.
New laptop | “I got a new laptop and can’t log in with my passkey” | Medium | 1. Helpdesk: confirm user has alternate method (mobile passkey or physical key) 2. User: log in from mobile device or physical key 3. User: navigate to identity provider security settings 4. User: register new device-bound passkey on new laptop 5. Admin: remove old laptop passkey if applicable | User has no alternate method → Admin: MFA reset | IT should trigger passkey re-enrollment as part of device provisioning workflow.
Lost / stolen device | “My laptop was stolen” or “I lost my phone” | High | 1. Admin: revoke passkey associated with lost device via admin console 2. Admin: revoke active sessions for the user 3. Helpdesk: confirm user can authenticate via remaining method 4. User: re-enroll replacement device when available | Device contained only registered passkey → Admin: urgent MFA reset and review access logs for suspicious activity | Ensure users know to report lost devices immediately. Include in security awareness training.
AUTHENTICATION ERRORS
Wrong method prompted | “It asks me to enter a USB key, but I didn’t configure one” | Low | 1. User: select “Try another way” or equivalent option 2. User: choose correct method (fingerprint, PIN, authenticator app) 3. Helpdesk: if no alternate option shown, check if passkey registration completed successfully | No alternate methods available and user cannot authenticate → Admin: MFA reset | During onboarding, confirm users complete setup and test login before cutover.
Passkey not recognized | “I’m using my fingerprint, but it says the passkey is not found” | Medium | 1. Helpdesk: verify user is on the correct device where passkey was registered 2. Helpdesk: prompt user to check OS and browser are up to date 3. User: try alternate browser 4. Admin: re-register passkey if corrupted | Persists after re-registration → escalate to platform / IdP support | Include minimum OS/browser versions in user documentation.
Cross-device login fails | “I can’t log in from another device using my passkey” | Low | 1. Helpdesk: explain that device-bound passkeys only work on the device where they were registered 2. User: log in from the original device 3. User: add a second passkey on the new device, or use QR code cross-device flow if supported | User needs access urgently and has no other method → Admin: MFA reset | Communicate clearly during rollout that device-bound passkeys are per-device. Encourage registering multiple methods.
LOCKOUT / RECOVERY
Complete lockout | “I can’t log in at all — none of my methods work” | High | 1. Helpdesk: verify user identity through out-of-band channel (video call, manager confirmation) 2. Admin: reset MFA / passkey registration 3. User: re-enroll from scratch 4. Helpdesk: ensure user registers at least two methods this time | Identity verification fails or circumstances are suspicious → Security team review | Require minimum of two registered methods as policy. Block single-method configurations if possible.
Admin lockout | “Our admin is locked out and can’t reset anyone else” | Critical | 1. Admin: use break-glass account (if configured) 2. Admin: contact identity provider support with org verification 3. Admin: follow documented emergency access procedure | No break-glass account exists → IdP vendor support required | Configure and test break-glass accounts before rollout. Store recovery credentials securely (e.g., safe, escrow).
Hardware key lost | “I lost my hardware security key” | Medium | 1. Admin: revoke the lost token in admin console 2. User: authenticate via alternate method (laptop passkey, authenticator app) 3. Admin: issue replacement token if applicable 4. User: register new token | Token was sole method → Admin: MFA reset required | Advise users with physical tokens to register a second key. Budget for replacements.
ONBOARDING / SETUP
Setup confusion | “I don’t understand what I’m supposed to do” | Low | 1. Helpdesk: direct user to self-service setup guide on intranet 2. Helpdesk: walk user through step-by-step if needed 3. User: use self-test tool to verify setup | N/A — resolve at helpdesk | Include clear visual guides for each OS. Offer office hours during rollout periods.
Biometric refusal | “I don’t want to use my fingerprint / face for work access” | Low | 1. Helpdesk: reassure user that biometric data never leaves the device and is not transmitted to the org 2. Helpdesk: offer PIN as alternative local verification method 3. Helpdesk: offer physical token if available | N/A — resolve at helpdesk | Proactively address biometric concerns in rollout comms. Always offer non-biometric alternatives.
BYOD refusal | “I don’t want a work app on my personal phone” | Low | 1. Helpdesk: explain that a phone is not required 2. Helpdesk: offer device-bound passkey on laptop only 3. Helpdesk: offer physical token as alternative 4. Helpdesk: if app is used, explain it only verifies identity and cannot access personal data | N/A — resolve at helpdesk | Include non-mobile options in all comms. Don’t assume everyone will use their phone.
PLATFORM-SPECIFIC
Unsupported device / OS | “My phone is too old” or “Passkeys don’t work on my Android” | Medium | 1. Helpdesk: check device against supported OS list 2. Helpdesk: if unsupported, offer laptop-only passkey or physical token 3. Helpdesk: document the exception | Widespread model incompatibility discovered → Project team review | Publish supported device list before rollout. Test across device diversity in pilot.
VM / VDI incompatibility | “I work in a VM, and passkeys don’t work there” | Medium | 1. Helpdesk: confirm this is a known exception 2. Admin: apply approved fallback authentication method per exception policy 3. Helpdesk: document the user and use case | New VM use case not covered by exception policy → Security team review | Identify VM/VDI users before rollout. Pre-approve fallback methods.
Platform limits reached | “I can’t add another passkey” | Low | 1. Helpdesk: check if user has hit platform maximum (e.g., 10 passkeys) 2. User: review and remove old/unused registrations 3. User: re-register | N/A — resolve at helpdesk | Document platform limits in setup guides. Advise users to clean up old methods periodically.